Project Plan

AI-Powered Branch-Wise Psychometric & Soft-Skills Assessment Platform

Version 1.0  |  Prepared for Development Handover

# Table of Contents

# 1. Project Summary

This plan sequences the build of the psychometric assessment platform described in the Business & Functional Requirements Document (BRD) and the Technical Requirements Document (TRD). Delivery is organized into 6 phases across an estimated 14–16 weeks for a v1 launch, using an agile approach with 2-week sprints from Phase 2 onward.

# 2. Recommended Team

| Role | Allocation | Primary Responsibility |
| --- | --- | --- |
| Product Owner | Part-time, full duration | Requirements sign-off, prioritization, SME liaison |
| Full-Stack Developer (Lead) | Full-time, full duration | Frontend + Supabase schema/Edge Functions |
| Frontend Developer | Full-time, weeks 3–14 | Assessment UI, admin console, candidate dashboard |
| Backend/Supabase Developer | Full-time, weeks 1–14 | Schema, RLS policies, Edge Functions, auth |
| Prompt/AI Engineer | Part-time, weeks 3–14 | Gemini prompt design for questions, scoring, reports |
| Psychometric SME | Part-time, weeks 1–4 and ongoing | Question bank validation, skill-weight review, rubric design |
| QA Engineer | Part-time, weeks 6–16 | Test plan execution, regression testing |
| UI/UX Designer | Part-time, weeks 1–4 | Wireframes, report PDF layout, design system |

# 3. Phase Breakdown

## Phase 0 — Discovery & Setup (Week 1)

- Finalize BRD/TRD sign-off with stakeholders.

- Set up GitHub repository, branching strategy, Supabase project, Gemini API access.

- Define initial launch scope: which programs/disciplines ship in v1 (recommend 3–5 programs, 2–3 disciplines each).

## Phase 1 — Content & Data Foundation (Weeks 2–4)

- SME authors/curates the core validated question bank per skill domain.

- Define skill domains and initial discipline-skill weight mappings for launch disciplines.

- Design and review the report tone/style guide with sample outputs.

- Finalize Supabase schema (tables, relationships, RLS policies) per TRD.

## Phase 2 — Core Platform Build, Sprint 1–2 (Weeks 5–8)

- Candidate auth, program/discipline selection flow.

- Assessment engine: branching logic, question retrieval, session state persistence.

- Core question rendering UI (Likert, MCQ/SJT, open-text).

## Phase 3 — AI Integration, Sprint 3–4 (Weeks 9–11)

- Gemini integration for scenario rewriting (Edge Function).

- Gemini integration for open-text rubric scoring with structured JSON output.

- Gemini integration for final report synthesis (strengths/growth areas/narrative) with tone-guideline enforcement.

- Prompt testing and iteration with SME review of sample outputs.

## Phase 4 — Reporting & Admin Console, Sprint 5 (Weeks 12–13)

- PDF report generation and rendering pipeline.

- Candidate dashboard (history, downloads).

- Admin console: question bank management, discipline/weight management, new-discipline approval workflow.

## Phase 5 — QA, Pilot & Hardening (Weeks 14–15)

- Full regression test pass (see Test Plan).

- Security review: RLS policy audit, API key exposure check, consent flow review.

- Pilot with a small candidate group (e.g., 20–50 students across launch disciplines); collect feedback.

- SME review of a sample of real generated reports for tone-guideline compliance.

## Phase 6 — Launch & Stabilization (Week 16)

- Production deployment (GitHub Pages + Supabase production project).

- Monitoring/alerting in place for Edge Function errors and Gemini API failures.

- Post-launch support window and backlog grooming for v1.1.

# 4. Milestone Summary

| Week | Milestone | Exit Criteria |
| --- | --- | --- |
| 1 | Project kickoff complete | Repos, Supabase project, Gemini access, scope locked |
| 4 | Content foundation ready | Question bank + skill weights approved by SME |
| 8 | Core assessment flow functional (no AI yet) | Candidate can complete a static assessment end-to-end |
| 11 | AI integration complete | Scenario rewriting, scoring, and report synthesis working in staging |
| 13 | Admin console & PDF reports complete | Admin can manage content; PDF report generated automatically |
| 15 | Pilot complete | Pilot feedback incorporated; tone/security review passed |
| 16 | v1 Launch | Production live, monitoring active |

# 5. Risk Register

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Gemini output breaks tone guidelines (discouraging language slips through) | High | Medium | Fixed system prompt + schema validation + SME spot-checks before wider rollout |
| Gemini API downtime/rate limits during peak usage | Medium | Medium | Fallback to generic (non-AI-flavored) scenario text; queue/retry logic |
| Question bank not psychometrically validated in time | High | Medium | Lock SME review as a hard gate before Phase 2 sign-off |
| Scope creep (Pymetrics-style games, Yoodli-style speech analysis) | Medium | High | Explicitly out-of-scope for v1 in BRD; park in v2 backlog |
| Data privacy/compliance gaps | High | Low | Dedicated Data Privacy review in Phase 5 before launch |
| API cost overrun from live generation | Medium | Medium | Cache/reuse generated scenario variants; monitor usage from day 1 |

# 6. Dependencies

- Access to Gemini API key with sufficient quota before Phase 3 begins.

- SME availability in Weeks 1–4 is on the critical path — delays here delay everything downstream.

- GitHub organization and Supabase project provisioned in Week 1.

# 7. Assumptions

- Team works in 2-week sprints from Phase 2 onward with sprint reviews and demos.

- Design system/wireframes are approved before frontend build begins in Phase 2.

- Pilot group availability is arranged in advance by the Product Owner.